## Sheet1
Task | Status | Predicted Time | Actual Time | Limitations
Requirements Doc | Complete
Architecture Diagram of Program | Complete
EasyOCR implementation | Complete
PyTesseract Implementation | Complete
TrOCR Implementation | Complete
Donut + LayoutLMv3 Implementation | Complete
DocTR Implementation | Complete | 1 hour | 1 hour 30 mins
Formal Evaluation Of Implementations | Complete | 20 mins | 15 mins
Finalizing Wrapper Class Implementation to leverage all OCRs | Complete | 2 hour | 1 hour 40 mins | lack of paid tools or good LLMs blunts accuracies in final class, OCR/layout based isn't the most efficient
Optimization For More Low Quality scanned invoices | Complete | 1 hour | 30 mins | PDF optimization is tedious, works well for pngs and jpegs but results are inconsistent in the PDF realm
Updating this checklist | Complete | 15 mins | 15 mins
Generating CSV File for Testing | Complete | 5 mins | 5 mins
Backend Testing + PostgreSQL integration | Mostly Complete | 2 hours | 3 hours 30 mins | AWS free tier has run out for 2 accounts now
Discussion about next steps | Not Started
UI implementation | Not Started
More Testing | Not Started